## 00_README
WHO Regional Office for Africa
Access to Medicines Tracking System - IGAP and Dementia country implementation
Version 2.0 (restructured) - Disease Prevention and Control cluster, NCD and Mental Health team
PURPOSE | Track, for each participating country, (i) the implementation of the WHO/HAI medicine price, availability, affordability and price components survey, and (ii) the resulting access-to-medicines results indicators for neurological disorders and dementia, in a form that can be aggregated to the regional level and reported against IGAP 2022-2031, the global dementia action plan 2017-2025 and the WHO health system building blocks.
SCOPE | Six countries at present: Botswana, Cote d'Ivoire, Ethiopia, Gambia, Malawi, Zambia. The structure is designed to scale to any number of countries without changing any formula.
HOW TO USE
1. Country register | Sheet 01. One row per country. Update focal point, phase and reporting dates here only.
2. Milestone catalogue | Sheet 02. The reference list of 31 milestones, their means of verification and their weight. Do not delete rows; add new milestones at the end and extend the tracker accordingly.
3. Progress tracker | Sheet 03. The single source of truth for implementation status: one row per country and per milestone. Fill Status, Planned date, Actual date, Evidence reference and Verified. Everything else is calculated.
4. Matrix view | Sheet 04. Read-only country-by-milestone view rebuilt by formula from sheet 03, for meetings and printing. Never type into the coloured status area.
5. Results framework | Sheet 05. The access-to-medicines indicators themselves (availability, price, affordability, policy and coverage). Enter baseline, target and each measurement round.
6. Indicator metadata | Sheet 06. Full definition of every indicator in sheet 05: numerator, denominator, method, source, periodicity, disaggregation and global framework alignment. Read before entering any value.
7. Tracer basket | Sheet 07. The medicines and care products actually surveyed, anchored on the WHO Model List of Essential Medicines (24th list, 2025), the WHO/HAI global and sub-Saharan Africa core lists and GDO indicator 10.
8. Regional dashboard | Sheet 08. Regional roll-up, fully formula-driven. No manual entry.
9. Risk register | Sheet 09. Likelihood x impact scoring, owner, review date and residual risk.
10. Data quality log | Sheet 10. Every data issue raised, its resolution and who cleared it.
11. Reference lists | Sheet 11. Controlled vocabularies behind the drop-down lists. Edit here to change any list.
STATUS CODES | NS = not started ¦ IP = in progress ¦ C = completed ¦ D = delayed (started, past planned date, not completed) ¦ NA = not applicable to this country. Verification is a separate field: a milestone is C when the activity is done and V(erified) = Yes when the means of verification has been received and filed.
PROGRESS MEASURES | Two measures are reported, and they are not interchangeable. Milestone completion rate = milestones coded C divided by applicable milestones (strict, audit-friendly). Weighted progress index = sum(weight x score) / sum(weight of applicable milestones), where C = 1.00, IP = 0.50, D = 0.25, NS = 0.00. The 0.50 and 0.25 conventions are arbitrary but explicit; they are declared here so that the figure can be reproduced by anyone.
COLOUR LEGEND | Navy header = structure, do not modify. Yellow cell = manual entry expected. White cell with a formula = calculated, do not overwrite. Grey italic = illustrative example, delete before use.
DATA STATUS WARNING | All implementation statuses carried over from version 1.0 (dated May 2024) are marked 'v1 carry-over, unverified' in the tracker. They must be re-confirmed with each country focal point and each means of verification filed before the matrix is used for reporting. No value in this workbook should be quoted externally until column 'Verified' reads Yes.
METHODOLOGICAL REFERENCES
R1 | WHO and Health Action International. Measuring medicine prices, availability, affordability and price components. 2nd ed. Geneva: WHO; 2008.
R2 | WHO. Intersectoral global action plan on epilepsy and other neurological disorders 2022-2031. Geneva: WHO; 2023.
R3 | WHO. Global action plan on the public health response to dementia 2017-2025. Geneva: WHO; 2017.
R4 | WHO. The Global Dementia Observatory Reference Guide. Geneva: WHO; 2018 (WHO/MSD/MER/18.1).
R5 | WHO. Monitoring the building blocks of health systems: a handbook of indicators and their measurement strategies. Geneva: WHO; 2010, section 4 (access to essential medicines).
R6 | WHO. Model List of Essential Medicines, 24th list. Geneva: WHO; 2025.
R7 | WHO. The selection and use of essential medicines. Technical Report Series No. 1064. Geneva: WHO; 2025.
R8 | WHO. mhGAP guideline for mental, neurological and substance use disorders. Geneva: WHO; 2023 update.
CHANGE LOG
v1.0 | Original consultant submission, four sheets (implementation dashboard, milestone matrix, regional dashboard, risk tracker).
v2.0 | Restructured into a normalised data model; results indicators added; indicator metadata added; tracer medicines basket added; all roll-ups converted to formulas; controlled vocabularies and validation added; date and formula defects of v1 corrected; data quality log opened.

## 01_Country_Register
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 01 - Country register
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
ISO3 | Country (official short name) | Project stream | Survey type | National focal point (name) | Institution | Focal point e-mail | WHO country office focal point | Project start date | Planned survey completion | Current phase | Reporting period of last update | Date of last update | Data confirmed by country (Yes/No)
BWA | Botswana | IGAP | National (WHO/HAI) | Dr K. Kgosi | Ministry of Health |  |  | 2024-01-15 |  | P3 Data collection |  |  | No
MWI | Malawi | IGAP | National (WHO/HAI) | Dr M. Banda | Ministry of Health |  |  | 2024-02-01 |  | P2 Preparation |  |  | No
CIV | Côte d'Ivoire | IGAP | National (WHO/HAI) | Dr A. Kone | Ministry of Health |  |  | 2024-01-10 |  | P4 Data management and analysis |  |  | No
ETH | Ethiopia | IGAP | National (WHO/HAI) | Dr T. Bekele | Ministry of Health |  |  | 2023-11-01 |  | P4 Data management and analysis |  |  | No
ZMB | Zambia | IGAP | National (WHO/HAI) | Dr C. Chanda | Ministry of Health |  |  | 2024-01-20 |  | P2 Preparation |  |  | No
GMB | Gambia | Dementia | National (WHO/HAI) | Dr S. Jallow | Ministry of Health |  |  | 2024-03-01 |  | P1 Governance and inception |  |  | No
Focal point names and start dates are carried over from version 1.0 and must be re-confirmed. Project stream for Cote d'Ivoire, Ethiopia and Zambia was recorded as 'Access to Medicines' in v1, which is the project name and not a stream; provisional value entered is IGAP, to be confirmed.

## 02_Milestone_Catalogue
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 02 - Milestone catalogue (reference list)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Milestone ID | Phase | Milestone | Milestone indicator | Means of verification | Primary responsibility | Method reference | Weight
M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed | Signed agreement or exchange of letters on file | Country agreement | AFRO / WCO | R1 s2.2 | 1
M02 | P1 Governance and inception | National inception meeting conducted | Inception meeting held with MoH and partners | Meeting report and attendance list | WCO / MoH | R1 s2.2 | 1
M03 | P1 Governance and inception | National technical working group established and operational | TWG constituted with written terms of reference | TOR and member list | MoH | R1 s2.4 | 1
M04 | P1 Governance and inception | Survey manager and area supervisors designated | Survey management team named in writing | Designation letters | MoH | R1 s2.4 | 1
M05 | P1 Governance and inception | Costed survey workplan and budget approved | Approved budget and timeline available | Signed workplan and budget | MoH / WCO | R1 s2.5 | 1
M06 | P1 Governance and inception | Ethics or administrative clearance obtained | Clearance granted by the competent national body | Clearance certificate | MoH | R1 s3.1 | 1
M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) | Scope and sectors documented in the protocol | Approved survey protocol | TWG | R1 s3.1.1 | 1
M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) | Survey areas selected per the standard sampling rule | Sampling plan with area list | Survey manager | R1 s3.1.3 | 1
M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities | At least five outlets per sector per area, 30 per sector | Outlet sampling frame | Survey manager | R1 s3.1.4 | 1
M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) | Final medicine list approved and exclusions justified | Approved medicine list (see sheet 07) | TWG | R1 s3.1.5 | 1
M11 | P2 Preparation | Originator brand product identified for each survey medicine | Originator brand and manufacturer identified per medicine | Medicine identification table | Survey manager | R1 s3.2 | 1
M12 | P2 Preparation | International reference prices obtained for the year preceding the survey | MSH international reference price file secured | Reference price file with year | Survey manager | R1 s3.3 | 1
M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured | Country-specific forms generated from the workbook | Generated data collection forms | Survey manager | R1 s3.4 | 1
M14 | P2 Preparation | Data collectors and area supervisors trained | Percentage of planned surveyors trained | Training report and attendance list | Survey manager | R1 s4.1 | 1
M15 | P2 Preparation | Pilot test conducted and tools revised | Pilot completed and revisions documented | Pilot report | Survey manager | R1 s4.2 | 1
M16 | P3 Data collection | Fieldwork launched | First facility visit recorded | Field mission order and first day logs | Area supervisors | R1 s4.3 | 1
M17 | P3 Data collection | Public sector procurement prices collected centrally | Procurement price file obtained from central medical stores | Procurement price extract | Survey manager | R1 s4.4 | 1
M18 | P3 Data collection | Facility data collection completed, including back-up facilities | Percentage of sampled outlets visited | Facility visit log | Area supervisors | R1 s4.3 | 1
M19 | P3 Data collection | Price components survey completed across the five supply chain stages | Price components data collected for tracer medicines | Price components forms | Survey manager | R1 s4.5 | 1
M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets | Percentage of outlets re-surveyed and concordance rate | Validation re-survey report | Area supervisors | R1 s4.6 | 1
M21 | P4 Data management and analysis | Double data entry completed and cross-checked | Two independent entries reconciled | Entry reconciliation log | Data manager | R1 s5.1 | 1
M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved | All flagged values verified or corrected | Data checker output and resolution log | Data manager | R1 s5.2 | 1
M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) | Analysis outputs generated from the workbook | Analysis workbook and output tables | Data manager | R1 s6 | 1
M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format | Draft report circulated to the TWG | Draft report | Survey manager | R1 s7 | 1
M25 | P5 Validation and policy translation | National validation workshop conducted | Workshop held and comments consolidated | Workshop report | MoH / TWG | R1 s7 | 1
M26 | P5 Validation and policy translation | Final report approved and disseminated | Report endorsed by the national authority and shared | Final report and dissemination note | MoH | R1 s7 | 1
M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed | Costed action plan drafted from survey findings | Draft action plan | TWG | R1 s11 | 1
M28 | P5 Validation and policy translation | Action plan endorsed by the national authority | Endorsement recorded | Endorsement letter or minutes | MoH | R1 s11 | 1
M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting | Tracer medicines reported through LMIS or DHIS2 | Routine reporting extract | MoH / HIS unit | R5 s4.2 | 1
M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed | Country submission made | Submission confirmation | MoH / WCO | R2 4.1 / R4 | 1
M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated | First quarterly review held | Quarterly progress report | WCO / AFRO | R5 | 1
Weight: relative importance of the milestone in the weighted progress index. Default 1 for every milestone. Change the weight here only, never in the tracker.

## 03_Progress_Tracker
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 03 - Progress tracker (single source of truth, one row per country and milestone)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Key | ISO3 | Country | Milestone ID | Phase | Milestone | Planned date | Actual date | Status | Weight | Score | Means of verification received (reference or link) | Verified | Responsible | Comment / next action | Last updated | Milestone indicator value (where quantitative)
BWA¦M01 | BWA | Botswana | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M02 | BWA | Botswana | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M03 | BWA | Botswana | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M04 | BWA | Botswana | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M05 | BWA | Botswana | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M06 | BWA | Botswana | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M07 | BWA | Botswana | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M08 | BWA | Botswana | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M09 | BWA | Botswana | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M10 | BWA | Botswana | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M11 | BWA | Botswana | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M12 | BWA | Botswana | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M13 | BWA | Botswana | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M14 | BWA | Botswana | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M15 | BWA | Botswana | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
BWA¦M16 | BWA | Botswana | M16 | P3 Data collection | Fieldwork launched |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
BWA¦M17 | BWA | Botswana | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M18 | BWA | Botswana | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M19 | BWA | Botswana | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M20 | BWA | Botswana | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M21 | BWA | Botswana | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M22 | BWA | Botswana | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M23 | BWA | Botswana | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M24 | BWA | Botswana | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M25 | BWA | Botswana | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M26 | BWA | Botswana | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M27 | BWA | Botswana | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M28 | BWA | Botswana | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
BWA¦M29 | BWA | Botswana | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M30 | BWA | Botswana | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
BWA¦M31 | BWA | Botswana | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M01 | MWI | Malawi | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M02 | MWI | Malawi | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
MWI¦M03 | MWI | Malawi | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
MWI¦M04 | MWI | Malawi | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M05 | MWI | Malawi | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M06 | MWI | Malawi | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M07 | MWI | Malawi | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
MWI¦M08 | MWI | Malawi | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
MWI¦M09 | MWI | Malawi | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M10 | MWI | Malawi | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M11 | MWI | Malawi | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M12 | MWI | Malawi | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M13 | MWI | Malawi | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
MWI¦M14 | MWI | Malawi | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M15 | MWI | Malawi | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M16 | MWI | Malawi | M16 | P3 Data collection | Fieldwork launched |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M17 | MWI | Malawi | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M18 | MWI | Malawi | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M19 | MWI | Malawi | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M20 | MWI | Malawi | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M21 | MWI | Malawi | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M22 | MWI | Malawi | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M23 | MWI | Malawi | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M24 | MWI | Malawi | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M25 | MWI | Malawi | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M26 | MWI | Malawi | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M27 | MWI | Malawi | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M28 | MWI | Malawi | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
MWI¦M29 | MWI | Malawi | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M30 | MWI | Malawi | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
MWI¦M31 | MWI | Malawi | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M01 | CIV | Côte d'Ivoire | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M02 | CIV | Côte d'Ivoire | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M03 | CIV | Côte d'Ivoire | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M04 | CIV | Côte d'Ivoire | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M05 | CIV | Côte d'Ivoire | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M06 | CIV | Côte d'Ivoire | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M07 | CIV | Côte d'Ivoire | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M08 | CIV | Côte d'Ivoire | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M09 | CIV | Côte d'Ivoire | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M10 | CIV | Côte d'Ivoire | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M11 | CIV | Côte d'Ivoire | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M12 | CIV | Côte d'Ivoire | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M13 | CIV | Côte d'Ivoire | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M14 | CIV | Côte d'Ivoire | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M15 | CIV | Côte d'Ivoire | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M16 | CIV | Côte d'Ivoire | M16 | P3 Data collection | Fieldwork launched |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M17 | CIV | Côte d'Ivoire | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M18 | CIV | Côte d'Ivoire | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
CIV¦M19 | CIV | Côte d'Ivoire | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M20 | CIV | Côte d'Ivoire | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M21 | CIV | Côte d'Ivoire | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
CIV¦M22 | CIV | Côte d'Ivoire | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
CIV¦M23 | CIV | Côte d'Ivoire | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M24 | CIV | Côte d'Ivoire | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M25 | CIV | Côte d'Ivoire | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M26 | CIV | Côte d'Ivoire | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M27 | CIV | Côte d'Ivoire | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M28 | CIV | Côte d'Ivoire | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
CIV¦M29 | CIV | Côte d'Ivoire | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M30 | CIV | Côte d'Ivoire | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
CIV¦M31 | CIV | Côte d'Ivoire | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ETH¦M01 | ETH | Ethiopia | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M02 | ETH | Ethiopia | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M03 | ETH | Ethiopia | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M04 | ETH | Ethiopia | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M05 | ETH | Ethiopia | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M06 | ETH | Ethiopia | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M07 | ETH | Ethiopia | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M08 | ETH | Ethiopia | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M09 | ETH | Ethiopia | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M10 | ETH | Ethiopia | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M11 | ETH | Ethiopia | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M12 | ETH | Ethiopia | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M13 | ETH | Ethiopia | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M14 | ETH | Ethiopia | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M15 | ETH | Ethiopia | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M16 | ETH | Ethiopia | M16 | P3 Data collection | Fieldwork launched |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M17 | ETH | Ethiopia | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M18 | ETH | Ethiopia | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M19 | ETH | Ethiopia | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M20 | ETH | Ethiopia | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M21 | ETH | Ethiopia | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M22 | ETH | Ethiopia | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M23 | ETH | Ethiopia | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ETH¦M24 | ETH | Ethiopia | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
ETH¦M25 | ETH | Ethiopia | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ETH¦M26 | ETH | Ethiopia | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ETH¦M27 | ETH | Ethiopia | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ETH¦M28 | ETH | Ethiopia | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ETH¦M29 | ETH | Ethiopia | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M30 | ETH | Ethiopia | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ETH¦M31 | ETH | Ethiopia | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M01 | ZMB | Zambia | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M02 | ZMB | Zambia | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ZMB¦M03 | ZMB | Zambia | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ZMB¦M04 | ZMB | Zambia | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M05 | ZMB | Zambia | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M06 | ZMB | Zambia | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M07 | ZMB | Zambia | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
ZMB¦M08 | ZMB | Zambia | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
ZMB¦M09 | ZMB | Zambia | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M10 | ZMB | Zambia | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M11 | ZMB | Zambia | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M12 | ZMB | Zambia | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M13 | ZMB | Zambia | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
ZMB¦M14 | ZMB | Zambia | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | D | 1 | 0.25 |  | No |  | v1 carry-over, unverified
ZMB¦M15 | ZMB | Zambia | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | D | 1 | 0.25 |  | No |  | v1 carry-over, unverified
ZMB¦M16 | ZMB | Zambia | M16 | P3 Data collection | Fieldwork launched |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M17 | ZMB | Zambia | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M18 | ZMB | Zambia | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M19 | ZMB | Zambia | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M20 | ZMB | Zambia | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M21 | ZMB | Zambia | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M22 | ZMB | Zambia | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M23 | ZMB | Zambia | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M24 | ZMB | Zambia | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M25 | ZMB | Zambia | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M26 | ZMB | Zambia | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M27 | ZMB | Zambia | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M28 | ZMB | Zambia | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
ZMB¦M29 | ZMB | Zambia | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M30 | ZMB | Zambia | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
ZMB¦M31 | ZMB | Zambia | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M01 | GMB | Gambia | M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M02 | GMB | Gambia | M02 | P1 Governance and inception | National inception meeting conducted |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
GMB¦M03 | GMB | Gambia | M03 | P1 Governance and inception | National technical working group established and operational |  |  | C | 1 | 1 |  | No |  | v1 carry-over, unverified
GMB¦M04 | GMB | Gambia | M04 | P1 Governance and inception | Survey manager and area supervisors designated |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M05 | GMB | Gambia | M05 | P1 Governance and inception | Costed survey workplan and budget approved |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M06 | GMB | Gambia | M06 | P1 Governance and inception | Ethics or administrative clearance obtained |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M07 | GMB | Gambia | M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) |  |  | IP | 1 | 0.5 |  | No |  | v1 carry-over, unverified
GMB¦M08 | GMB | Gambia | M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M09 | GMB | Gambia | M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M10 | GMB | Gambia | M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M11 | GMB | Gambia | M11 | P2 Preparation | Originator brand product identified for each survey medicine |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M12 | GMB | Gambia | M12 | P2 Preparation | International reference prices obtained for the year preceding the survey |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M13 | GMB | Gambia | M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M14 | GMB | Gambia | M14 | P2 Preparation | Data collectors and area supervisors trained |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M15 | GMB | Gambia | M15 | P2 Preparation | Pilot test conducted and tools revised |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M16 | GMB | Gambia | M16 | P3 Data collection | Fieldwork launched |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M17 | GMB | Gambia | M17 | P3 Data collection | Public sector procurement prices collected centrally |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M18 | GMB | Gambia | M18 | P3 Data collection | Facility data collection completed, including back-up facilities |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M19 | GMB | Gambia | M19 | P3 Data collection | Price components survey completed across the five supply chain stages |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M20 | GMB | Gambia | M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M21 | GMB | Gambia | M21 | P4 Data management and analysis | Double data entry completed and cross-checked |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M22 | GMB | Gambia | M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M23 | GMB | Gambia | M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M24 | GMB | Gambia | M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M25 | GMB | Gambia | M25 | P5 Validation and policy translation | National validation workshop conducted |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M26 | GMB | Gambia | M26 | P5 Validation and policy translation | Final report approved and disseminated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M27 | GMB | Gambia | M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M28 | GMB | Gambia | M28 | P5 Validation and policy translation | Action plan endorsed by the national authority |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified
GMB¦M29 | GMB | Gambia | M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M30 | GMB | Gambia | M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed |  |  | NS | 1 | 0 |  | No |  | New in v2 - to be assessed with the country focal point
GMB¦M31 | GMB | Gambia | M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated |  |  | NS | 1 | 0 |  | No |  | v1 carry-over, unverified

## 04_Matrix_View
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 04 - Country by milestone matrix (read only, rebuilt from sheet 03)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
|  | ISO3 join key - do not edit | BWA | MWI | CIV | ETH | ZMB | GMB
Milestone ID | Phase | Milestone | Botswana (IGAP) | Malawi (IGAP) | Côte d'Ivoire (IGAP) | Ethiopia (IGAP) | Zambia (IGAP) | Gambia (Dementia)
M01 | P1 Governance and inception | Country formally confirmed and terms of participation agreed | NS | NS | NS | NS | NS | NS
M02 | P1 Governance and inception | National inception meeting conducted | C | C | C | C | C | C
M03 | P1 Governance and inception | National technical working group established and operational | C | C | C | C | C | C
M04 | P1 Governance and inception | Survey manager and area supervisors designated | NS | NS | NS | NS | NS | NS
M05 | P1 Governance and inception | Costed survey workplan and budget approved | NS | NS | NS | NS | NS | NS
M06 | P1 Governance and inception | Ethics or administrative clearance obtained | NS | NS | NS | NS | NS | NS
M07 | P2 Preparation | Survey scope agreed (national or sub-national, sectors covered) | C | C | C | C | IP | IP
M08 | P2 Preparation | Six survey areas selected (main urban centre plus five areas) | C | IP | C | C | IP | NS
M09 | P2 Preparation | Medicine outlet sample drawn per sector, including back-up facilities | NS | NS | NS | NS | NS | NS
M10 | P2 Preparation | Survey medicine list finalised (global core, regional core, supplementary tracer basket) | NS | NS | NS | NS | NS | NS
M11 | P2 Preparation | Originator brand product identified for each survey medicine | NS | NS | NS | NS | NS | NS
M12 | P2 Preparation | International reference prices obtained for the year preceding the survey | NS | NS | NS | NS | NS | NS
M13 | P2 Preparation | Data collection forms and WHO/HAI workbook Part I and Part II configured | C | IP | C | C | C | NS
M14 | P2 Preparation | Data collectors and area supervisors trained | C | NS | C | C | D | NS
M15 | P2 Preparation | Pilot test conducted and tools revised | C | NS | C | C | D | NS
M16 | P3 Data collection | Fieldwork launched | IP | NS | C | C | NS | NS
M17 | P3 Data collection | Public sector procurement prices collected centrally | NS | NS | NS | NS | NS | NS
M18 | P3 Data collection | Facility data collection completed, including back-up facilities | NS | NS | C | C | NS | NS
M19 | P3 Data collection | Price components survey completed across the five supply chain stages | NS | NS | NS | NS | NS | NS
M20 | P3 Data collection | Supervisor validation re-survey completed in at least 20 percent of outlets | NS | NS | NS | NS | NS | NS
M21 | P4 Data management and analysis | Double data entry completed and cross-checked | NS | NS | IP | C | NS | NS
M22 | P4 Data management and analysis | Workbook data checker run and flagged values resolved | NS | NS | IP | C | NS | NS
M23 | P4 Data management and analysis | Analysis completed (availability, price ratios, affordability, price components) | NS | NS | NS | C | NS | NS
M24 | P4 Data management and analysis | Draft survey report prepared in the standard reporting format | NS | NS | NS | IP | NS | NS
M25 | P5 Validation and policy translation | National validation workshop conducted | NS | NS | NS | NS | NS | NS
M26 | P5 Validation and policy translation | Final report approved and disseminated | NS | NS | NS | NS | NS | NS
M27 | P5 Validation and policy translation | Costed policy action plan on access to medicines developed | NS | NS | NS | NS | NS | NS
M28 | P5 Validation and policy translation | Action plan endorsed by the national authority | NS | NS | NS | NS | NS | NS
M29 | P5 Validation and policy translation | Tracer medicines integrated into routine health information reporting | NS | NS | NS | NS | NS | NS
M30 | P5 Validation and policy translation | Country reporting to the Global Dementia Observatory or IGAP country reporting completed | NS | NS | NS | NS | NS | NS
M31 | P5 Validation and policy translation | Quarterly implementation monitoring initiated | NS | NS | NS | NS | NS | NS
|  | Applicable milestones (excluding NA) | 31 | 31 | 31 | 31 | 31 | 31
|  | Milestones completed (C) | 7 | 3 | 9 | 12 | 3 | 2
|  | Milestones in progress (IP) | 1 | 2 | 2 | 1 | 2 | 1
|  | Milestones delayed (D) | 0 | 0 | 0 | 0 | 2 | 0
|  | Milestone completion rate | 22.58% | 9.677% | 29.03% | 38.71% | 9.677% | 6.452%
|  | Weighted progress index | 24.19% | 12.9% | 32.26% | 40.32% | 14.52% | 8.065%
|  | Evidence verified (share of completed milestones) | 0% | 0% | 0% | 0% | 0% | 0%

## 05_Results_Framework
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 05 - Results framework (access to medicines indicators, one block per country)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Indicator code | Domain | Indicator | Unit | Global framework alignment | Direction | ISO3 | Country | Measurement round | Baseline value | Baseline year | Target value | Target year | Value for this round | Measurement date | Data source | Data quality flag | Comment
A1 | Availability | EXAMPLE ROW - illustrative format only, delete before use | % | IGAP target 2.2 | Higher is better | XXX | Example country | Round 1 (2026) | 28% | 2024 | 80% | 2031 | 34% | 2026-06-30 | WHO/HAI survey 2026 | Provisional | Public sector, 8 tracer antiseizure medicines
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | BWA | Botswana | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | BWA | Botswana | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | BWA | Botswana | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | BWA | Botswana | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | BWA | Botswana | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | BWA | Botswana | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | BWA | Botswana | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | BWA | Botswana | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | BWA | Botswana | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | BWA | Botswana | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | BWA | Botswana | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | BWA | Botswana | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | BWA | Botswana | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | BWA | Botswana | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | BWA | Botswana | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | BWA | Botswana | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | BWA | Botswana | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | BWA | Botswana | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | BWA | Botswana | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | BWA | Botswana | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | BWA | Botswana | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | BWA | Botswana | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | BWA | Botswana | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | BWA | Botswana | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | BWA | Botswana | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | BWA | Botswana | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | BWA | Botswana | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | BWA | Botswana | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | BWA | Botswana | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | BWA | Botswana | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | BWA | Botswana | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | BWA | Botswana | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | BWA | Botswana | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | BWA | Botswana | Baseline
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | MWI | Malawi | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | MWI | Malawi | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | MWI | Malawi | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | MWI | Malawi | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | MWI | Malawi | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | MWI | Malawi | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | MWI | Malawi | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | MWI | Malawi | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | MWI | Malawi | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | MWI | Malawi | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | MWI | Malawi | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | MWI | Malawi | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | MWI | Malawi | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | MWI | Malawi | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | MWI | Malawi | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | MWI | Malawi | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | MWI | Malawi | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | MWI | Malawi | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | MWI | Malawi | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | MWI | Malawi | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | MWI | Malawi | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | MWI | Malawi | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | MWI | Malawi | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | MWI | Malawi | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | MWI | Malawi | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | MWI | Malawi | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | MWI | Malawi | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | MWI | Malawi | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | MWI | Malawi | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | MWI | Malawi | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | MWI | Malawi | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | MWI | Malawi | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | MWI | Malawi | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | MWI | Malawi | Baseline
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | CIV | Côte d'Ivoire | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | CIV | Côte d'Ivoire | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | CIV | Côte d'Ivoire | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | CIV | Côte d'Ivoire | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | CIV | Côte d'Ivoire | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | CIV | Côte d'Ivoire | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | CIV | Côte d'Ivoire | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | CIV | Côte d'Ivoire | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | CIV | Côte d'Ivoire | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | CIV | Côte d'Ivoire | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | CIV | Côte d'Ivoire | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | CIV | Côte d'Ivoire | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | CIV | Côte d'Ivoire | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | CIV | Côte d'Ivoire | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | CIV | Côte d'Ivoire | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | CIV | Côte d'Ivoire | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | CIV | Côte d'Ivoire | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | CIV | Côte d'Ivoire | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | CIV | Côte d'Ivoire | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | CIV | Côte d'Ivoire | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | CIV | Côte d'Ivoire | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | CIV | Côte d'Ivoire | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | CIV | Côte d'Ivoire | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | CIV | Côte d'Ivoire | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | CIV | Côte d'Ivoire | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | CIV | Côte d'Ivoire | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | CIV | Côte d'Ivoire | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | CIV | Côte d'Ivoire | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | CIV | Côte d'Ivoire | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | CIV | Côte d'Ivoire | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | CIV | Côte d'Ivoire | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | CIV | Côte d'Ivoire | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | CIV | Côte d'Ivoire | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | CIV | Côte d'Ivoire | Baseline
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | ETH | Ethiopia | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | ETH | Ethiopia | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | ETH | Ethiopia | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | ETH | Ethiopia | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | ETH | Ethiopia | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | ETH | Ethiopia | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | ETH | Ethiopia | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | ETH | Ethiopia | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | ETH | Ethiopia | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | ETH | Ethiopia | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | ETH | Ethiopia | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | ETH | Ethiopia | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | ETH | Ethiopia | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | ETH | Ethiopia | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | ETH | Ethiopia | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | ETH | Ethiopia | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | ETH | Ethiopia | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | ETH | Ethiopia | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | ETH | Ethiopia | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | ETH | Ethiopia | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | ETH | Ethiopia | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | ETH | Ethiopia | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | ETH | Ethiopia | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | ETH | Ethiopia | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | ETH | Ethiopia | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | ETH | Ethiopia | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | ETH | Ethiopia | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | ETH | Ethiopia | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | ETH | Ethiopia | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | ETH | Ethiopia | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | ETH | Ethiopia | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | ETH | Ethiopia | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | ETH | Ethiopia | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | ETH | Ethiopia | Baseline
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | ZMB | Zambia | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | ZMB | Zambia | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | ZMB | Zambia | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | ZMB | Zambia | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | ZMB | Zambia | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | ZMB | Zambia | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | ZMB | Zambia | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | ZMB | Zambia | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | ZMB | Zambia | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | ZMB | Zambia | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | ZMB | Zambia | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | ZMB | Zambia | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | ZMB | Zambia | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | ZMB | Zambia | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | ZMB | Zambia | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | ZMB | Zambia | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | ZMB | Zambia | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | ZMB | Zambia | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | ZMB | Zambia | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | ZMB | Zambia | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | ZMB | Zambia | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | ZMB | Zambia | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | ZMB | Zambia | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | ZMB | Zambia | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | ZMB | Zambia | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | ZMB | Zambia | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | ZMB | Zambia | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | ZMB | Zambia | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | ZMB | Zambia | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | ZMB | Zambia | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | ZMB | Zambia | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | ZMB | Zambia | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | ZMB | Zambia | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | ZMB | Zambia | Baseline
A1 | Availability | Mean availability of the tracer basket for neurological disorders, public sector | % | IGAP target 2.2 | Higher is better | GMB | Gambia | Baseline
A2 | Availability | Mean availability of the tracer basket for neurological disorders, private sector | % | IGAP target 2.2 | Higher is better | GMB | Gambia | Baseline
A3 | Availability | Mean availability of the 14 global core medicines, public sector | % | Building blocks core indicator 1 | Higher is better | GMB | Gambia | Baseline
A4 | Availability | Mean availability of the 14 global core medicines, private sector | % | Building blocks core indicator 1 | Higher is better | GMB | Gambia | Baseline
A5 | Availability | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | % | IGAP target 2.2 | Higher is better | GMB | Gambia | Baseline
A6 | Availability | Mean availability of the dementia comorbidity and care basket, public sector | % | Dementia action plan action area 4 | Higher is better | GMB | Gambia | Baseline
A7 | Availability | Mean stockout duration of tracer medicines in the past six months, public warehouses | days | Building blocks section 4 | Lower is better | GMB | Gambia | Baseline
B1 | Price | Median price ratio, lowest priced generic, public sector procurement | ratio | Building blocks core indicator 2 | Lower is better | GMB | Gambia | Baseline
B2 | Price | Median price ratio, lowest priced generic, public sector patient price | ratio | Building blocks core indicator 2 | Lower is better | GMB | Gambia | Baseline
B3 | Price | Median price ratio, lowest priced generic, private sector | ratio | Building blocks core indicator 2 | Lower is better | GMB | Gambia | Baseline
B4 | Price | Median price ratio, originator brand, private sector | ratio | Building blocks core indicator 2 | Lower is better | GMB | Gambia | Baseline
B5 | Price | Brand premium (originator brand price divided by lowest priced generic price), private sector | ratio | WHO/HAI section 6 | Lower is better | GMB | Gambia | Baseline
B6 | Price | Total percentage mark-up between manufacturer selling price and patient price | % | Building blocks indicator 9 | Lower is better | GMB | Gambia | Baseline
C1 | Affordability | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | days' wages | WHO/HAI section 6.4 | Lower is better | GMB | Gambia | Baseline
C2 | Affordability | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | days' wages | WHO/HAI section 6.4 | Lower is better | GMB | Gambia | Baseline
C3 | Affordability | Share of the tracer basket costing more than one day's wage for a 30 day course | % | WHO/HAI section 6.4 | Lower is better | GMB | Gambia | Baseline
D1 | Policy and system | National medicines policy exists and has been updated within the past five years | Yes/No | Building blocks indicator 2 | Yes | GMB | Gambia | Baseline
D2 | Policy and system | National essential medicines list exists and has been updated within the past five years | Yes/No | Building blocks indicator 3 | Yes | GMB | Gambia | Baseline
D3 | Policy and system | Number of tracer basket medicines included in the national essential medicines list | count | EML 24th list | Higher is better | GMB | Gambia | Baseline
D4 | Policy and system | Neurological disorders included in the universal health coverage benefit package | Yes/No | IGAP target 2.1 | Yes | GMB | Gambia | Baseline
D5 | Policy and system | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Yes/No | IGAP target 2.2 | Yes | GMB | Gambia | Baseline
D6 | Policy and system | At least one antidementia medicine approved by the national medicines regulatory authority | Yes/No | GDO indicator 10, Q10x1 | Yes | GMB | Gambia | Baseline
D7 | Policy and system | Generic version of at least one antidementia medicine available | Yes/No | GDO indicator 10, Q10x1x1 | Yes | GMB | Gambia | Baseline
D8 | Policy and system | At least one antidementia medicine reimbursable for on-label use | Yes/No/Partial | GDO indicator 10, Q10x1x2 | Yes | GMB | Gambia | Baseline
D9 | Policy and system | Care products and assistive technologies for dementia available or reimbursable (three categories) | count 0-3 | GDO indicator 10 checklist | Higher is better | GMB | Gambia | Baseline
D10 | Policy and system | Legal provisions allow or encourage generic substitution in the private sector | Yes/No | Building blocks indicator 4 | Yes | GMB | Gambia | Baseline
D11 | Policy and system | Access to essential medicines recognised in the constitution or national legislation | Yes/No | Building blocks indicator 1 | Yes | GMB | Gambia | Baseline
E1 | Coverage and use | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | % | IGAP target 5.1 | Higher is better | GMB | Gambia | Baseline
E2 | Coverage and use | Share of people diagnosed with epilepsy receiving antiseizure medicines | % | IGAP target 5.1 cascade | Higher is better | GMB | Gambia | Baseline
E3 | Coverage and use | Diagnostic rate for dementia | % | GDO indicator 7 / dementia target 4 | Higher is better | GMB | Gambia | Baseline
E4 | Coverage and use | Share of prescriptions written by generic name in surveyed facilities | % | Building blocks section 4.2 | Higher is better | GMB | Gambia | Baseline
E5 | Coverage and use | Share of prescribed medicines drawn from the national essential medicines list | % | Building blocks section 4.2 | Higher is better | GMB | Gambia | Baseline
F1 | Financing | Public and private per capita expenditure on medicines | US$ per capita | Building blocks indicator 5 | Context | GMB | Gambia | Baseline
F2 | Financing | Share of the population covered by health insurance | % | Building blocks indicator 6 | Higher is better | GMB | Gambia | Baseline

## 06_Indicator_Metadata
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 06 - Indicator metadata (read before entering any value in sheet 05)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Indicator code | Indicator | Definition | Numerator | Denominator | Method of measurement and notes | Data source | Periodicity | Disaggregation | Global framework alignment | Reference | Source milestone
A1 | Mean availability of the tracer basket for neurological disorders, public sector | Mean percentage of surveyed public sector medicine outlets in which each medicine of the neurological tracer basket was found on the day of data collection, averaged over the medicines of the basket. | Sum of the availability percentages of each tracer medicine | Number of tracer medicines surveyed | Facility survey, day of visit, no stock recorded as zero. Reported separately for the lowest priced generic and the originator brand. | WHO/HAI medicine price and availability survey | Every 3 to 5 years | Sector, urban/rural, level of care, product type | IGAP target 2.2 | R2 | M23
A2 | Mean availability of the tracer basket for neurological disorders, private sector | Same definition as A1 applied to licensed private pharmacies and licensed drug stores. | Sum of the availability percentages of each tracer medicine | Number of tracer medicines surveyed | Facility survey, day of visit. | WHO/HAI survey | Every 3 to 5 years | Sector, urban/rural, product type | IGAP target 2.2 | R2 | M23
A3 | Mean availability of the 14 global core medicines, public sector | Mean availability of the 14 medicines of the WHO/HAI global core list, which allows international comparison. | Sum of the availability percentages of the 14 global core medicines | 14 | Standard core indicator. Amitriptyline and diazepam in the global core list are directly relevant to the mental and neurological basket. | WHO/HAI survey | Every 3 to 5 years | Sector, urban/rural | Building blocks core indicator 1 | R5 | M23
A4 | Mean availability of the 14 global core medicines, private sector | Same as A3 for the private sector. | Sum of availability percentages | 14 | Standard core indicator. | WHO/HAI survey | Every 3 to 5 years | Sector, urban/rural | Building blocks core indicator 1 | R5 | M23
A5 | Share of surveyed public outlets with at least one antiseizure medicine available on the day of visit | Percentage of surveyed public outlets holding at least one antiseizure medicine of the tracer basket on the day of visit. | Number of public outlets with at least one antiseizure medicine available | Number of public outlets surveyed | Direct operational proxy for the IGAP target 2.2 basket. Antiseizure medicines are the tracer medicines named in IGAP. | WHO/HAI survey | Every 3 to 5 years, annually if integrated into routine LMIS | Level of care, urban/rural | IGAP target 2.2 | R2 | M23
A6 | Mean availability of the dementia comorbidity and care basket, public sector | Mean availability of the dementia comorbidity and care basket (see sheet 07), noting that no antidementia medicine is currently on the WHO Model List of Essential Medicines. | Sum of availability percentages of basket medicines | Number of basket medicines surveyed | For dementia, availability of antidementia medicines is captured as a regulatory and reimbursement indicator (D6 to D8) rather than a facility availability indicator. | WHO/HAI survey and national regulatory data | Every 3 to 5 years | Sector, level of care | Dementia action plan action area 4 | R3 | M23
A7 | Mean stockout duration of tracer medicines in the past six months, public warehouses | Average number of days over the past six months during which a tracer medicine was out of stock in surveyed public warehouses. | Sum of stockout days per tracer medicine | Number of tracer medicines assessed | Requires stock record review at central and regional medical stores; a recall period of six months is used. | Warehouse record review, LMIS | Annual once integrated into routine reporting | Medicine, warehouse level | Building blocks section 4 | R5 | M23
B1 | Median price ratio, lowest priced generic, public sector procurement | Ratio between the median unit price paid by the government to procure the medicine and the corresponding international reference price. | Median local unit procurement price | MSH international reference price for the year preceding the survey | Computed in the WHO/HAI workbook. Reported separately for lowest priced generic and originator brand. | WHO/HAI survey, central procurement records | Every 3 to 5 years | Product type, medicine | Building blocks core indicator 2 | R5 | M23
B2 | Median price ratio, lowest priced generic, public sector patient price | Ratio between the median unit price charged to the patient in public facilities and the international reference price. | Median public sector patient unit price | MSH international reference price | Computed in the WHO/HAI workbook. | WHO/HAI survey | Every 3 to 5 years | Product type, medicine | Building blocks core indicator 2 | R5 | M23
B3 | Median price ratio, lowest priced generic, private sector | Ratio between the median unit price in private outlets and the international reference price, lowest priced generic. | Median private sector unit price, lowest priced generic | MSH international reference price | Core indicator of the health system building blocks handbook. | WHO/HAI survey | Every 3 to 5 years | Product type, medicine | Building blocks core indicator 2 | R5 | M23
B4 | Median price ratio, originator brand, private sector | Same as B3 for the originator brand product. | Median private sector unit price, originator brand | MSH international reference price | Core indicator. | WHO/HAI survey | Every 3 to 5 years | Medicine | Building blocks core indicator 2 | R5 | M23
B5 | Brand premium (originator brand price divided by lowest priced generic price), private sector | Ratio of the median originator brand price to the median lowest priced generic price for the same medicine, same sector. | Median originator brand unit price | Median lowest priced generic unit price | Quantifies the scope for savings through generic substitution; read together with indicator D10. | WHO/HAI survey | Every 3 to 5 years | Medicine, sector | WHO/HAI section 6 | R1 | M23
B6 | Total percentage mark-up between manufacturer selling price and patient price | Percentage by which the final patient price exceeds the manufacturer selling price or the cost, insurance and freight price, obtained by tracking tracer medicines through the five supply chain stages. | Patient price minus manufacturer selling price | Manufacturer selling price | Price components survey, stages 1 to 5 (manufacturer plus insurance and freight, landed price, wholesale or central medical stores price, retail or dispensary price, dispensed price). | WHO/HAI price components survey | Every 3 to 5 years | Stage of supply chain, sector, medicine | Building blocks indicator 9 | R5 | M23
C1 | Number of days' wages of the lowest paid unskilled government worker for 30 days of treatment with the lowest priced generic antiseizure medicine | Number of days' wages that the lowest paid unskilled government worker must spend to purchase a 30 day course of treatment with the lowest priced generic antiseizure medicine. | Total cost of a 30 day standard course | Daily wage of the lowest paid unskilled government worker | Standard treatment schedules must be fixed in the protocol before fieldwork and kept constant across rounds. A treatment requiring more than one day's wage is conventionally considered unaffordable. | WHO/HAI survey and national public service pay scale | Every 3 to 5 years | Medicine, sector, product type | WHO/HAI section 6.4 | R1 | M23
C2 | Number of days' wages for 30 days of treatment for a person with dementia and one comorbidity (standard basket) | Same method as C1 applied to a standard monthly basket for a person living with dementia and one comorbidity, as defined in sheet 07. | Total cost of the standard monthly basket | Daily wage of the lowest paid unskilled government worker | The basket composition must be recorded in the survey report so that the figure remains comparable. | WHO/HAI survey and national pay scale | Every 3 to 5 years | Sector, product type | WHO/HAI section 6.4 | R1 | M23
C3 | Share of the tracer basket costing more than one day's wage for a 30 day course | Share of tracer basket medicines whose 30 day course costs more than one day's wage of the lowest paid unskilled government worker. | Number of tracer medicines above the one day threshold | Number of tracer medicines priced | Summary affordability measure, easier to communicate than a distribution of days' wages. | WHO/HAI survey | Every 3 to 5 years | Sector, product type | WHO/HAI section 6.4 | R1 | M23
D1 | National medicines policy exists and has been updated within the past five years | Existence of an official national medicines policy, updated within the past five years. | Not applicable | Not applicable | Documentary review and key informant confirmation; record the year of the last update. | National authority, WHO pharmaceutical country profile | Every 4 years | Not applicable | Building blocks indicator 2 | R5 | M07 and M30
D2 | National essential medicines list exists and has been updated within the past five years | Existence of a national essential medicines list, updated within the past five years. | Not applicable | Not applicable | Documentary review; record the year of the last update. | National authority | Every 4 years | Not applicable | Building blocks indicator 3 | R5 | M07 and M30
D3 | Number of tracer basket medicines included in the national essential medicines list | Number of medicines of the tracer basket (sheet 07) that appear on the current national essential medicines list. | Number of tracer basket medicines on the national list | Not applicable | Compare the national list against the tracer basket medicine by medicine, including strength and dosage form. | National essential medicines list | At each revision of the national list | Therapeutic group, EML core or complementary | EML 24th list | R6 | M07 and M30
D4 | Neurological disorders included in the universal health coverage benefit package | Neurological disorders are named in the national universal health coverage benefit package. | Not applicable | Not applicable | Documentary review of the benefit package. | National authority | Every 2 to 3 years | Not applicable | IGAP target 2.1 | R2 | M07 and M30
D5 | Country reports essential medicines and basic technologies for neurological disorders available in primary care | Country reports that the core set of essential medicines and basic technologies for neurological disorders is available and affordable in primary care on a sustainable basis. | Not applicable | Not applicable | This is the reporting indicator behind IGAP global target 2.2. The facility survey indicators A1, A2 and A5 provide the evidence for the country response. | Country reporting to WHO | Every 3 years | Not applicable | IGAP target 2.2 | R2 | M07 and M30
D6 | At least one antidementia medicine approved by the national medicines regulatory authority | At least one antidementia medicine (donepezil, galantamine, rivastigmine or memantine) is approved by the national medicines regulatory authority. | Not applicable | Not applicable | Global Dementia Observatory question Q10x1. | National medicines regulatory authority | Every 2 years | Not applicable | GDO indicator 10, Q10x1 | R4 | M07 and M30
D7 | Generic version of at least one antidementia medicine available | A generic version of at least one approved antidementia medicine is available. | Not applicable | Not applicable | Global Dementia Observatory question Q10x1x1. | National medicines regulatory authority | Every 2 years | Not applicable | GDO indicator 10, Q10x1x1 | R4 | M07 and M30
D8 | At least one antidementia medicine reimbursable for on-label use | At least one approved antidementia medicine is reimbursable for on-label use. | Not applicable | Not applicable | Global Dementia Observatory question Q10x1x2, three response options: yes, no, partial. | National health financing authority | Every 2 years | Not applicable | GDO indicator 10, Q10x1x2 | R4 | M07 and M30
D9 | Care products and assistive technologies for dementia available or reimbursable (three categories) | Number of the three Global Dementia Observatory care product categories (adult hygiene products, assistive technology, housing adjustments) that are available or reimbursable. | Number of categories available or reimbursable | 3 | Global Dementia Observatory indicator 10 checklist. Record available and reimbursable separately in the comment field. | National authority, home care organisations | Every 2 years | Product category | GDO indicator 10 checklist | R4 | M07 and M30
D10 | Legal provisions allow or encourage generic substitution in the private sector | Existence of legal provisions allowing or encouraging generic substitution in the private sector. | Not applicable | Not applicable | Legal and regulatory review. | National authority | Every 4 years | Not applicable | Building blocks indicator 4 | R5 | M07 and M30
D11 | Access to essential medicines recognised in the constitution or national legislation | Access to essential medicines is recognised in the constitution or in national legislation as part of the right to health. | Not applicable | Not applicable | Review of the constitution and health legislation. | National legislation | Every 4 years | Not applicable | Building blocks indicator 1 | R5 | M07 and M30
E1 | Service coverage for epilepsy (people with epilepsy receiving services in the past 12 months) | Percentage of people with epilepsy who used services during the past 12 months. | Number of people with epilepsy in receipt of services | Estimated number of people with epilepsy in the population | IGAP indicator 5.1. Numerator from routine information systems or a facility survey; denominator from a national survey or sub-regional prevalence estimates. Countries may measure the cascade: diagnosed, on antiseizure medicines, seizure controlled. | Routine health information system, facility survey | Every 2 to 3 years | Sex, age, level of care | IGAP target 5.1 | R2 | M29 and M30
E2 | Share of people diagnosed with epilepsy receiving antiseizure medicines | Percentage of people diagnosed with epilepsy who have access to appropriate, affordable and safe antiseizure medicines. | Number of people diagnosed with epilepsy receiving antiseizure medicines | Number of people diagnosed with epilepsy | Second step of the IGAP 5.1 cascade; this is the indicator that links the medicine survey to service coverage. | Routine health information system, facility records | Annual where routine data allow | Sex, age | IGAP target 5.1 cascade | R2 | M29 and M30
E3 | Diagnostic rate for dementia | Number of people with dementia who have received a diagnosis, divided by the estimated number of people with dementia. | Number of people with dementia who received a diagnosis | Estimated population prevalence of dementia for the country | Global Dementia Observatory indicator 7 and global dementia action plan target 4. | Routine health information system, registries | Every 2 years | Sex, age | GDO indicator 7 / dementia target 4 | R4 | M29 and M30
E4 | Share of prescriptions written by generic name in surveyed facilities | Percentage of medicines prescribed by generic name in surveyed facilities. | Number of medicines prescribed by generic name | Total number of medicines prescribed | Standard rational use prescribing indicator, measured on a sample of prescriptions or encounters. | Prescription record review | Every 3 to 5 years | Level of care, sector | Building blocks section 4.2 | R5 | M29 and M30
E5 | Share of prescribed medicines drawn from the national essential medicines list | Percentage of prescribed medicines that appear on the national essential medicines list. | Number of prescribed medicines on the national list | Total number of medicines prescribed | Standard rational use prescribing indicator. | Prescription record review | Every 3 to 5 years | Level of care, sector | Building blocks section 4.2 | R5 | M29 and M30
F1 | Public and private per capita expenditure on medicines | Total pharmaceutical expenditure per capita, disaggregated into public and private financing. | Total pharmaceutical expenditure | Total population | From national health accounts. Reported in US dollars and in local currency. | National health accounts | Annual | Public and private financing | Building blocks indicator 5 | R5 | M30
F2 | Share of the population covered by health insurance | Percentage of the population covered by any form of health insurance. | Number of people covered by health insurance | Total population | Household survey or administrative records. | Household survey | Every 3 to 5 years | Sex, urban/rural, wealth quintile | Building blocks indicator 6 | R5 | M30

## 07_Tracer_Basket
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 07 - Tracer medicines and care products basket
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
ID | Category | International non-proprietary name | Strength | Dosage form | WHO Model List status (24th list, 2025) | Position in the survey medicine list | IGAP relevance | Dementia relevance | Included in the national survey (Yes/No) | On the national essential medicines list (Yes/No) | Notes
T01 | Antiseizure (IGAP core) | carbamazepine | 200 mg | tablet | EML 24th list, 5.1.1, core | Sub-Saharan Africa regional core list | Yes | Yes
T02 | Antiseizure (IGAP core) | phenobarbital | 30 mg | tablet | EML 24th list, 5.1.1, core | Supplementary | Yes | Yes
T03 | Antiseizure (IGAP core) | phenytoin | 100 mg | solid oral dosage form | EML 24th list, 5.1.1, core | Supplementary | Yes | Yes
T04 | Antiseizure (IGAP core) | valproic acid (sodium valproate) | 200 mg | enteric coated tablet | EML 24th list, 5.1.1, core | Supplementary | Yes | Yes
T05 | Antiseizure (IGAP core) | levetiracetam | 500 mg | tablet | EML 24th list, 5.1.1, core | Supplementary | Yes | Yes
T06 | Antiseizure (IGAP core) | lamotrigine | 100 mg | tablet | EML 24th list, 5.1.1, core (adjunctive use) | Supplementary | Yes | Yes
T07 | Antiseizure, emergency | diazepam | 5 mg | tablet | EML 24th list, 5.1.1, core | WHO/HAI global core list, item 11 | Yes | Yes
T08 | Antiseizure, emergency | diazepam rectal | 5 mg/mL | rectal solution or gel | EML 24th list, 5.1.1, core | Supplementary | Yes | Yes
T09 | Antiseizure, emergency | midazolam | 10 mg/mL | solution for oromucosal administration | EML 24th list, 5.1.1, core | Supplementary | Yes | No
T10 | Antidementia | donepezil | 5 mg / 10 mg | tablet | Not on the WHO Model List of Essential Medicines | Supplementary, national decision | No | Yes
T11 | Antidementia | memantine | 10 mg | tablet | Not on the WHO Model List of Essential Medicines | Supplementary, national decision | No | Yes
T12 | Antidementia | rivastigmine | 1.5 mg | capsule or patch | Not on the WHO Model List of Essential Medicines | Supplementary, national decision | No | Yes
T13 | Antidementia | galantamine | 8 mg | tablet | Not on the WHO Model List of Essential Medicines | Supplementary, national decision | No | Yes
T14 | Dementia comorbidity and behavioural symptoms | haloperidol | 5 mg | tablet | EML 24th list, 24.1, core | Supplementary | No | Yes
T15 | Dementia comorbidity and behavioural symptoms | risperidone | 1 mg | tablet | EML 24th list, 24.1, core | Supplementary | No | Yes
T16 | Dementia comorbidity and behavioural symptoms | fluoxetine | 20 mg | tablet or capsule | EML 24th list, 24.2.1, core | Supplementary | No | Yes
T17 | Dementia comorbidity and behavioural symptoms | amitriptyline | 25 mg | tablet | EML 24th list, 24.2.1, core | WHO/HAI global core list, item 6 | No | Yes
T18 | Vascular risk factor control | atenolol | 50 mg | tablet | EML 24th list, cardiovascular, core | WHO/HAI global core list, item 3 | Yes | Yes
T19 | Vascular risk factor control | simvastatin | 20 mg | tablet | EML 24th list, cardiovascular, core | WHO/HAI global core list, item 5 | Yes | Yes
T20 | Vascular risk factor control | glibenclamide | 5 mg | tablet | EML 24th list, antidiabetic, core | WHO/HAI global core list, item 2 | Yes | Yes
T21 | Care products (dementia) | adult hygiene products | not applicable | product category | Not applicable | Global Dementia Observatory indicator 10 | No | Yes
T22 | Care products (dementia) | assistive technology (walking frame, wheelchair, spectacles, hearing aid) | not applicable | product category | Not applicable | Global Dementia Observatory indicator 10 | No | Yes
T23 | Care products (dementia) | housing adjustments (ramps, grab bars, smoke detectors) | not applicable | product category | Not applicable | Global Dementia Observatory indicator 10 | No | Yes
No antidementia medicine (donepezil, galantamine, rivastigmine, memantine) appears on the WHO Model List of Essential Medicines, 24th list (2025). Access to these medicines therefore cannot be tracked as an essential medicines availability indicator; it is tracked through indicators D6 to D9, which follow the Global Dementia Observatory indicator 10 questions on regulatory approval, generic availability and reimbursement.
Antiseizure medicines are the tracer medicines named in IGAP for global target 2.2, which is why the basket is built around them.
Items T18 to T20 are already on the WHO/HAI global core list, so they are collected in any standard survey at no additional field cost; they are retained here because mid-life hypertension, diabetes and dyslipidaemia are modifiable dementia risk factors under action area 3 of the global dementia action plan.
Antipsychotic medicines T14 and T15 are included for availability monitoring only. The mhGAP guideline does not support their routine use for behavioural and psychological symptoms of dementia; the results report should state this explicitly so that availability is not read as an encouragement to prescribe.
Any medicine of the global or sub-Saharan Africa core list excluded from a national survey must be reported and justified in the survey report.

## 08_Regional_Dashboard
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 08 - Regional monitoring dashboard (calculated, no manual entry)
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Regional indicator | Definition applied | Value | Denominator | Coverage | Related global target
Countries engaged in the initiative | Countries listed in the country register | 6 | 6 | 100% | Project level
Countries having completed the inception phase | All milestones of phase P1 coded C | 0 | 6 | 0% | Project level
Countries with data collectors trained | Milestone M14 coded C | 3 | 6 | 50% | Project level
Countries having launched fieldwork | Milestone M16 coded C | 2 | 6 | 33.33% | Project level
Countries having completed data collection | Milestone M18 coded C | 2 | 6 | 33.33% | IGAP target 2.2: evidence base on availability of essential medicines for neurological disorders in primary care
Countries having completed the price components survey | Milestone M19 coded C | 0 | 6 | 0% | IGAP target 2.2 and WHO/HAI price components analysis
Countries with a validated final report | Milestone M26 coded C | 0 | 6 | 0% | Project level
Countries with a costed action plan developed | Milestone M27 coded C | 0 | 6 | 0% | Dementia action plan action area 1 and IGAP strategic objective 1
Countries with an endorsed action plan | Milestone M28 coded C | 0 | 6 | 0% | Dementia action plan action area 1 and IGAP strategic objective 1
Countries reporting tracer medicines through routine information systems | Milestone M29 coded C | 0 | 6 | 0% | IGAP target 4.1 and dementia target 6: routine collection and reporting of a core indicator set
Milestones completed, all countries | Count of C across the tracker | 36 | 186 | 19.35% | Project level
Milestones delayed, all countries | Count of D across the tracker | 2 | 186 | 1.075% | Project level
Completed milestones with the means of verification on file | C and verified equal to Yes | 0 | 36 | 0% | Data governance standard: 100 percent of completed milestones evidenced
Open risks rated high or extreme | Risk register, residual score of 12 or more and status not closed | 5 |  |  | Project level
Results indicators with a value recorded | Sheet 05, latest value not empty | 0 | 204 | 0% | IGAP target 4.1 and dementia target 6
Progress by country
Country | Phase | Milestone completion rate | Weighted progress index | Open risks | Highest inherent risk score
Botswana | P3 Data collection | 22.58% | 24.19% | 1 | 9
Malawi | P2 Preparation | 9.677% | 12.9% | 1 | 16
Côte d'Ivoire | P4 Data management and analysis | 29.03% | 32.26% | 1 | 9
Ethiopia | P4 Data management and analysis | 38.71% | 40.32% | 1 | 16
Zambia | P2 Preparation | 9.677% | 14.52% | 1 | 20
Gambia | P1 Governance and inception | 6.452% | 8.065% | 1 | 9

## 09_Risk_Register
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 09 - Risk register
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Risk ID | Date raised | Country | Category | Risk description | Likelihood (1-5) | Impact (1-5) | Inherent score | Rating | Mitigation action | Owner | Due date | Status | Date of last review | Residual score
RSK-01 |  | Botswana | Operational | Delay in approval of the facility sampling frame | 3 | 3 | 9 | Moderate | Engage the Ministry of Health lead to expedite sign-off of the sampling frame; provide the standard sampling note as supporting material. | Focal point and WHO country office | 2024-06-05 | Open
RSK-02 |  | Malawi | Financial | Insufficient budget for surveyor field travel | 4 | 4 | 16 | Extreme | Reprioritise travel logistics and explore joint supervision missions with the Ministry of Health; confirm the funding gap in writing. | Technical working group and WHO AFRO | 2024-06-15 | Open
RSK-03 |  | Côte d'Ivoire | Data quality | Discrepancies in public sector facility stock records | 3 | 3 | 9 | Moderate | Conduct a secondary verification sweep with national supervisors on the affected facilities; document all corrections in the data quality log. | Data manager | 2024-05-30 | In progress
RSK-04 |  | Ethiopia | Institutional | Competing national health priorities delaying the validation workshop | 4 | 4 | 16 | Extreme | Secure a fixed date in the Ministry of Health calendar and circulate the draft report in advance so that the workshop is a decision meeting. | Focal point and Ministry of Health | 2024-06-20 | Open
RSK-05 |  | Zambia | Regulatory | Administrative delay in ethics and administrative clearance | 4 | 5 | 20 | Extreme | Request a WHO AFRO support letter to accelerate the review; prepare all preparatory milestones in parallel so that fieldwork can start immediately after clearance. | WHO country office lead | 2024-05-25 | Open
RSK-06 |  | Gambia | Technical | Limited national expertise in adapting the survey protocol to dementia | 3 | 3 | 9 | Moderate | Provide direct technical assistance through the AFRO regional consultant and pair the country with a country already past the preparation phase. | AFRO consultant | 2024-06-10 | Open
RSK-07 |  | All countries | Data governance | Statuses carried over from version 1.0 have not been verified against a means of verification | 4 | 4 | 16 | Extreme | Re-confirm every status with the country focal point and file the means of verification before any external reporting. | AFRO monitoring focal point |  | Open
RSK-08 |  | All countries | Methodological | Standard treatment schedules and the reference price year are not yet fixed, which would make affordability and price ratios non comparable between countries and between rounds | 4 | 4 | 16 | Extreme | Fix the treatment schedules, the international reference price source and its year in a short regional methodological note before the next round of fieldwork. | AFRO monitoring focal point |  | Open
Likelihood and impact are scored 1 to 5. Inherent score = likelihood x impact. Rating: 1-5 low, 6-11 moderate, 12-14 high, 15-25 extreme. The residual score is entered after the mitigation action has been implemented and reviewed.

## 10_Data_Quality_Log
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 10 - Data quality log
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Issue ID | Source | Cell or field | Issue type | Description | Action taken or required | Status | Owner | Date closed
DQ-01 | v1 - Implementation Dashboard | D5 | Data type | Start date stored as a serial number and displayed as 45306, while other start dates in the same column were stored as text | Dates rebuilt as true date values with a single display format in sheet 01 | Resolved in v2
DQ-02 | v1 - Implementation Dashboard | F5:F10 | Consistency | Percentage completion entered by hand and inconsistent with the milestone count (Botswana 45 percent against 7 of 19 milestones, Ethiopia 75 percent against 12 of 19) | Progress is now calculated from the tracker; two explicit measures are reported | Resolved in v2
DQ-03 | v1 - M&E Milestone Matrix | C4:K4 | Formula | The status key cells beginning with an equals sign were interpreted as formulas and returned a name error | Key moved to the README sheet as plain text and enforced by data validation | Resolved in v2
DQ-04 | v1 - Regional Dashboard | C5:H5 | Logic | Countries supported was derived from the status of the inception meeting, which measures something else | Regional roll-up rebuilt on explicit milestone definitions stated next to each indicator | Resolved in v2
DQ-05 | v1 - all sheets | Country labels | Consistency | The Gambia and Gambia used in different sheets, which breaks any lookup | ISO3 codes introduced as the join key | Resolved in v2
DQ-06 | v1 - M&E Milestone Matrix | E6:J6 | Consistency | Project streams recorded as IGAP, AtM and Dementia, where AtM is the project name and not a stream | Provisional stream assigned in sheet 01, to be confirmed with each country | Open
DQ-07 | v1 - all sheets | All records | Currency of data | All statuses and dates date from May 2024 and no update has been recorded since | Re-confirm every record with the country focal points and record the reporting period in sheet 01 | Open
DQ-08 | v1 - M&E Milestone Matrix | Status codes | Definition | Status code V (validated) was defined but never used, and overlapped with C (completed) | Verification separated from status as its own field in the tracker | Resolved in v2
DQ-09 | v2 - Progress Tracker | Column L | Completeness | No means of verification is currently on file for any milestone coded completed | Collect and file the means of verification listed in sheet 02 for every completed milestone | Open
DQ-10 | v2 - Results Framework | All records | Completeness | No baseline value has been recorded for any access to medicines indicator | Establish baselines from the most recent national survey or set them at the first survey round | Open

## 11_Reference_Lists
WHO Regional Office for Africa - Access to Medicines Tracking System (IGAP / Dementia)
Sheet 11 - Controlled vocabularies
Version 2.0 - draft for technical review. Yellow cells are for data entry; white cells are calculated - do not overwrite.
Status code | Status meaning | Project stream | Survey type | Sector | Phase | Risk status | Data quality flag
NS | Not started | IGAP | National (WHO/HAI) | Public | P1 Governance and inception | Open | Final
IP | In progress | Dementia | Sub-national (WHO/HAI) | Private | P2 Preparation | In progress | Provisional
C | Completed | IGAP and Dementia | Facility census module | Mission or faith based | P3 Data collection | Escalated | Estimated
D | Delayed |  | Routine LMIS extraction | Dispensing doctors | P4 Data management and analysis | Closed | Not available
NA | Not applicable |  |  | Public procurement | P5 Validation and policy translation